## Maintenance_Records
Work Order | Date | Type | Description | Findings / Result | Tubes Plugged / Action | Cumulative Plugged Tubes (after job) | Performed By | Status | Downtime (hours) | Cost (INR lakh) | Follow-up
WO-2015-0311 | 2015-03-20 | Commissioning | Baseline thickness survey and hydrotest at commissioning | Baseline readings taken; hydrotest OK | None | 0 | In-house | Completed | 0 | 0 | None
WO-2016-0308 | 2016-03-12 | Preventive | Annual cleaning during short shutdown | Bundle hydrojetted; light fouling found | None | 0 | Contractor | Completed | 72 | 3.2 | None
WO-2017-0310 | 2017-03-14 | Preventive | Annual cleaning | Bundle hydrojetted; moderate shell-side fouling | None | 0 | Contractor | Completed | 84 | 3.6 | Consider additional online cleaning
WO-2019-0318 | 2019-03-18 | Turnaround | Full bundle pull, hydrojetting, ECT, hydrotest; pass partition gasket replaced | No tubes plugged; min wall 2.45 mm | None | 0 | Contractor + in-house | Completed | 336 | 42 | Inspect rows 1-4 at each opportunity
WO-2021-0517 | 2021-05-17 | Corrective | Channel-side gasket weep after start-up following minor trip | Channel gasket renewed; no tube damage | None | 0 | In-house | Completed | 30 | 1.1 | None
WO-2022-0826 | 2022-08-26 | Corrective | Minor external leak at shell flange | Studs re-torqued, gasket replaced online | None | 0 | In-house | Completed | 0 | 0.4 | None
WO-2023-1109 | 2023-11-09 | Inspection / repair | Opportunity shutdown: partial pull, 100 % ECT, plugging, hydrojetting, gasket | 4 tubes plugged; under-deposit corrosion rows 1-3 | Plugged 4 tubes | 4 | Contractor + in-house | Completed | 192 | 18.5 | Monitor rows 1-4; consider spare bundle if loss rate rises
WO-2024-0227 | 2024-02-27 | Corrective | Floating head cover gasket renewed during short outage | No leakage after restart | None | 4 | In-house | Completed | 36 | 2 | None
WO-2025-0414 | 2025-04-14 | Inspection / repair | Planned 10-day shutdown: ECT, hydrojetting, plugging, pass partition gasket replaced | 7 tubes plugged; min wall 2.14 mm; tubesheet pitting 0.4 mm | Plugged 7 tubes | 11 | Contractor + in-house | Completed | 240 | 24 | Replace bundle at Feb 2027 turnaround; order spare
WO-2025-0614 | 2025-06-14 | Emergency corrective | Emergency shutdown after off-spec diesel; shell-side hydrotest, leak location, tube plugging, gasket renewed | 14 leaking tubes found in rows 1-4; plugged | Plugged 14 tubes | 25 | Contractor + in-house | Completed | 144 | 31.5 | Bundle replacement urgent; quarterly ECT screening
WO-2025-0915 | 2025-09-15 | Condition monitoring | Thermography and DP trend review; quarterly ECT screening (rows 1-6) | No new leak indicated; readings stable | None | 25 | In-house | Completed | 0 | 0.6 | Continue quarterly
WO-2025-1215 | 2025-12-15 | Condition monitoring | Quarterly ECT screening (rows 1-6) | Stable | None | 25 | In-house | Completed | 0 | 0.6 | Continue quarterly
WO-2026-0213 | 2026-02-13 | Preventive | Calibration of DP transmitters and product sulphur correlation alarm test | Completed; alarm functional | None | 25 | Instrumentation | Completed | 0 | 0.3 | None
WO-2026-0316 | 2026-03-16 | Condition monitoring | Quarterly ECT screening (rows 1-6) | Stable | None | 25 | In-house | Completed | 0 | 0.6 | Continue quarterly
WO-2026-0528 | 2026-05-28 | Receipt | Receipt inspection of new tube bundle at stores (Tender 0412); nitrogen purge verified | Accepted with minor packing damage noted | None | 25 | Stores + Inspection | Completed | 0 | 0.2 | Six-monthly storage inspection due Nov 2026
WO-2026-0618 | 2026-06-18 | Condition monitoring | Quarterly ECT screening (rows 1-6) | Stable; no new plugging required | None | 25 | In-house | Completed | 0 | 0.6 | Next round due Sep 2026
WO-2027-0201 | 2027-02-01 | Planned replacement | Install new tube bundle in DHDT shutdown (planned) | Not yet executed | Replace bundle | 0 | Contractor + in-house | Planned | 0 | 0 | Approval of shutdown window pending
Summary
Completed work orders | 16
Total downtime, completed jobs (hours) | 1134
Total cost, completed jobs (INR lakh) | 129.2
Corrective + emergency jobs | 4
Latest cumulative plugged tubes (completed jobs, from WO-2026-0618) | 25
Plugged share of 640 tubes | 3.906%
SYNTHETIC / DUMMY DATA. MRPL used as demo setting only. The last row is a planned, not completed, job. Costs are illustrative.