## Tender_Register
Tender No | Title | Department | NIT / Published Date | Estimated Cost (INR crore) | Bid Due Date | Bid Opening Date | Documents Purchased (count) | Bids Received (count) | Status | Awardee | Awarded Value (INR crore) | Related Equipment / Remarks
MRPL/PUR/MECH/2025-26/0388 | Hydrojetting and cleaning services for heat exchanger bundles (rate contract) | Mechanical | 2025-06-18 | 1.6 | 2025-07-30 | 2025-07-31 | 3 | 2 | Under evaluation |  |  | Multiple exchangers, incl. DHDT Unit-31
MRPL/PUR/MECH/2025-26/0405 | Supply of gaskets and fasteners for heat exchangers (rate contract) | Mechanical | 2025-07-01 | 0.85 | 2025-08-08 | 2025-08-08 | 1 | 1 | Awarded | Sahyadri Fabricators Pvt Ltd | 0.79 | Various
MRPL/PUR/MECH/2025-26/0412 | Supply of replacement tube bundle (spare) for feed/effluent heat exchanger 31-E-102A, DHDT Unit-31 | Mechanical | 2025-07-12 | 4.2 | 2025-08-11 | 2025-08-12 | 6 | 4 | Awarded - delivered, installation pending | Vishwa Thermal Engineering Pvt Ltd | 3.79 | 31-E-102A
MRPL/PUR/INST/2025-26/0398 | Calibration and testing of pressure safety valves, Units 31-34 | Instrumentation | 2025-07-14 | 1.1 | 2025-08-14 | 2025-08-14 | 1 | 1 | Awarded | Aravalli Valve Services | 0.98 | PSVs, DHDT area
MRPL/PUR/CHEM/2025-26/0421 | Supply of filming corrosion inhibitor, cooling water system | Chemicals | 2025-07-28 | 0.65 | 2025-09-01 | 2025-09-02 | 0 | 0 | Awarded | Tulu Specialty Chemicals | 0.61 | Cooling water
MRPL/PUR/ELEC/2025-26/0430 | Rewinding of HT motors, 3.3 kV (rate contract) | Electrical | 2025-08-05 | 0.9 | 2025-09-10 | 2025-09-11 | 0 | 0 | Awarded | Malabar Motors and Drives | 0.86 | HT motors
MRPL/PUR/CIV/2024-25/0731 | Cooling tower fill replacement, CT-2 | Civil | 2024-07-12 | 2.3 | 2024-08-12 | 2024-08-13 | 0 | 0 | Completed | Konkan Cooling Systems | 2.18 | CT-2 (NIT also dated 12 July, but in 2024)
SYNTHETIC / DUMMY DATA. MRPL used as demo setting only; vendors, values and tender numbers are fictional. Blue = typed inputs.
Note: Tender 0388 was published earlier (18 Jun 2025) but two firms bought its documents on 12 Jul 2025. Tender 0412 was published on 12 Jul 2025.

## Doc_Purchase_Log
Purchase ID | Tender No | Firm | City | Purchase Date | Fee incl. GST (INR) | Bid Submitted
PUR-0001 | MRPL/PUR/MECH/2025-26/0388 | Konkan Reactor Services | Mangaluru | 2025-06-24 | 5900 | No
PUR-0002 | MRPL/PUR/MECH/2025-26/0388 | Sahyadri Fabricators Pvt Ltd | Belagavi | 2025-07-12 | 5900 | Yes
PUR-0003 | MRPL/PUR/MECH/2025-26/0388 | Vishwa Thermal Engineering Pvt Ltd | Pune | 2025-07-12 | 5900 | Yes
PUR-0004 | MRPL/PUR/MECH/2025-26/0405 | Sahyadri Fabricators Pvt Ltd | Belagavi | 2025-07-04 | 2950 | Yes
PUR-0005 | MRPL/PUR/MECH/2025-26/0412 | Vishwa Thermal Engineering Pvt Ltd | Pune | 2025-07-12 | 5900 | Yes
PUR-0006 | MRPL/PUR/MECH/2025-26/0412 | Coastal Exchangers & Vessels Ltd | Vadodara | 2025-07-12 | 5900 | Yes
PUR-0007 | MRPL/PUR/MECH/2025-26/0412 | Nordhaus-Rao Process Equipment (India) Pvt Ltd | Hyderabad | 2025-07-12 | 5900 | Yes
PUR-0008 | MRPL/PUR/MECH/2025-26/0412 | Kaveri Heat Transfer Systems | Chennai | 2025-07-14 | 5900 | Yes
PUR-0009 | MRPL/PUR/MECH/2025-26/0412 | Sahyadri Fabricators Pvt Ltd | Belagavi | 2025-07-16 | 5900 | No
PUR-0010 | MRPL/PUR/MECH/2025-26/0412 | Meridian Industrial Works | Ahmedabad | 2025-07-21 | 5900 | No
PUR-0011 | MRPL/PUR/INST/2025-26/0398 | Aravalli Valve Services | Jaipur | 2025-07-15 | 5900 | Yes

## Bid_Evaluation_0412
Bidder | Technical Status | Quoted Price (INR crore) | Delivery (weeks) | Estimate (INR crore) | Variance vs Estimate | Rank (qualified bids) | Remarks
Vishwa Thermal Engineering Pvt Ltd | Qualified | 3.87 | 30 | 4.2 | -7.857% | 1 | Negotiated to 3.79 crore on 17 Sep 2025; awarded
Coastal Exchangers & Vessels Ltd | Qualified | 4.05 | 32 | 4.2 | -3.571% | 2 | L2
Kaveri Heat Transfer Systems | Qualified | 4.31 | 28 | 4.2 | 2.619% | 3 | L3; fastest delivery
Nordhaus-Rao Process Equipment (India) Pvt Ltd | Disqualified | 3.62 | 34 | 4.2 | -13.81% | n/a | Indicative price only; did not meet alloy-bundle experience criterion; price bid not opened
Negotiated award value (INR crore) |  | 3.79
Reduction from L1 quote |  | 2.067%
Award value vs estimate |  | -9.762%